## Project Dashboard
HONG KONG CAD RADAR PROJECT — PROJECT MONITORING DASHBOARD
Civil Aviation Department ¦ 5-Phase Radar System Implementation ¦ PMP Compliant
PROJECT INFORMATION
Project Name | Client | PM | Code | Value | Start | End | Status
HK CAD Radar System Modernization | CAD,HK | TBD | CAD-RADAR-2025 | HK$850M | 2025-07-01 | 2029-06-30 | In Progress
PHASE OVERVIEW
Phase | Name | Start | End | Days | Budget (HK$) | Actual (HK$) | % Done | Status | RAG
1 | Initiation | 2025-07-01 | 2025-12-31 | 184 | 42.5M | 38.2M | 95% | Done | Green
2 | Design | 2026-01-01 | 2026-12-31 | 365 | 170M | 95M | 60% | Active | Green
3 | Installation | 2027-01-01 | 2027-12-31 | 365 | 340M | 0 | 0% | Pending | Grey
4 | Testing | 2028-01-01 | 2028-12-31 | 365 | 127.5M | 0 | 0% | Pending | Grey
5 | Handover | 2029-01-01 | 2029-06-30 | 182 | 170M | 0 | 0% | Pending | Grey
KEY PERFORMANCE INDICATORS
KPI | Target | Actual | Variance | Unit | Status | Trend | PMP Area | Frequency | Owner
SPI | 1.00 | 0.98 | -0.02 | Ratio | On Track | Up | Schedule | Weekly | PM
CPI | 1.00 | 1.05 | +0.05 | Ratio | Favorable | Up | Cost | Weekly | PM
Scope Changes | <10 | 3 | -7 | Count | Favorable | Down | Scope | Monthly | PM
Defect Density | <0.5 | 0.3 | -0.2 | Def/KLOC | Favorable | Down | Quality | Monthly | QA
Risk Score | <50 | 35 | -15 | Score | OK | Flat | Risk | Monthly | RM
Stakeholder Sat | >80% | 85% | +5% | % | Favorable | Up | Stakeholder | Quarterly | PM
Safety Incidents | 0 | 0 | 0 | Count | Perfect | Flat | Safety | Weekly | SO
Milestone On-Time | >90% | 92% | +2% | % | Favorable | Up | Schedule | Monthly | PM
BAC | HK$850M | HK$850M | 0 | HK$ | On Budget | Flat | Cost | Monthly | PM
EAC | HK$850M | HK$809M | -41M | HK$ | Favorable | Up | Cost | Monthly | PM
EARNED VALUE MANAGEMENT (EVM)
Metric | PV | EV | AC | SV | CV | SPI | CPI
Cumulative | 212.5M | 208.25M | 198.33M | -4.25M | +9.92M | 0.980 | 1.050
Current Period | 17M | 16.66M | 15.88M | -0.34M | +0.78M | 0.980 | 1.050
EAC | — | — | — | — | 809M | — | —
VAC | — | — | — | +41M | — | — | —
TCPI | — | — | — | — | — | — | 1.02

## Phase 1 - Initiation
PHASE 1: INITIATION & PLANNING
WORK BREAKDOWN STRUCTURE
WBS ID | Task Name | Duration (Days) | Start | End | Predecessor | Assigned To | % Complete | Status | Deliverable | RAG | Notes
1.1 | Project Charter Dev | 14 | 2025-07-01 | 2025-07-14 | — | Sponsor | 100% | Done | Charter | Green | Approved
1.2 | Stakeholder ID | 21 | 2025-07-01 | 2025-07-21 | — | PM | 100% | Done | Register | Green | 47 identified
1.3 | Requirements Gathering | 42 | 2025-07-15 | 2025-08-25 | 1.1 | BA Team | 100% | Done | Req Doc | Green | 215 reqs
1.4 | Feasibility Study | 30 | 2025-07-22 | 2025-08-20 | 1.2 | Eng Lead | 100% | Done | Report | Green | Confirmed
1.5 | Site Survey | 28 | 2025-08-01 | 2025-08-28 | 1.2 | Site Eng | 100% | Done | Survey Report | Green | 3 sites
1.6 | Environmental Impact | 35 | 2025-08-15 | 2025-09-18 | 1.4 | Env Cons | 100% | Done | EIA Report | Green | EPD approved
1.7 | Risk Assessment | 28 | 2025-08-26 | 2025-09-22 | 1.3,1.4 | Risk Mgr | 100% | Done | Risk Register | Green | 68 risks
1.8 | Budget Estimation | 21 | 2025-09-01 | 2025-09-21 | 1.4 | Cost Eng | 100% | Done | Cost Est | Green | HK$850M
1.9 | Project Plan Dev | 30 | 2025-09-15 | 2025-10-14 | 1.3,1.7 | PM | 100% | Done | PMP | Green | PMBOK 7th
1.10 | Regulatory Approval | 45 | 2025-09-23 | 2025-11-06 | 1.6,1.8 | PM | 100% | Done | CAD Approval | Green | Obtained
1.11 | Phase Gate Review | 7 | 2025-11-15 | 2025-11-21 | 1.9,1.10 | Steering | 100% | Done | Gate Approval | Green | Authorized
1.12 | Lessons Learned | 10 | 2025-11-22 | 2025-12-01 | 1.11 | PM | 90% | In Progress | LL Report | Green | Draft done

## Phase 2 - Design
PHASE 2: DESIGN & PROCUREMENT
WORK BREAKDOWN STRUCTURE
WBS ID | Task Name | Duration (Days) | Start | End | Predecessor | Assigned To | % Complete | Status | Deliverable | RAG | Notes
2.1 | System Architecture | 60 | 2026-01-01 | 2026-03-01 | 1.11 | Architect | 85% | In Progress | Arch Doc | Green | On schedule
2.2 | Radar Tech Specs | 45 | 2026-01-15 | 2026-02-28 | 2.1 | Tech Lead | 75% | In Progress | Tech Spec | Green | ASR-12
2.3 | SSR Design | 45 | 2026-02-01 | 2026-03-17 | 2.1 | Comms Eng | 65% | In Progress | SSR Doc | Amber | Mode S delay
2.4 | MLAT Design | 40 | 2026-02-15 | 2026-03-26 | 2.1 | Nav Eng | 50% | In Progress | MLAT Doc | Green | 4 stations
2.5 | Data Processing Design | 55 | 2026-03-01 | 2026-04-24 | 2.1 | SW Arch | 40% | In Progress | SW Doc | Green | Asterix
2.6 | Site Prep Design | 50 | 2026-03-15 | 2026-05-03 | 2.2,2.3 | Civil Eng | 30% | In Progress | Plans | Green | 3 sites
2.7 | RFP Preparation | 35 | 2026-04-01 | 2026-05-05 | 2.2 | Procurement | 25% | In Progress | RFP Docs | Green | 3 packages
2.8 | Tender Evaluation | 60 | 2026-05-06 | 2026-07-04 | 2.7 | Board | 0% | Pending | Eval Report | Grey
2.9 | Contract Award | 30 | 2026-07-05 | 2026-08-03 | 2.8 | Legal | 0% | Pending | Contracts | Grey
2.10 | FAT Plan | 28 | 2026-06-01 | 2026-06-28 | 2.2,2.3 | QA | 0% | Pending | FAT Plan | Grey
2.11 | SAT Plan | 28 | 2026-06-15 | 2026-07-12 | 2.4,2.5 | QA | 0% | Pending | SAT Plan | Grey
2.12 | PDR Review | 14 | 2026-04-25 | 2026-05-08 | 2.1,2.2 | CAD/PM | 0% | Pending | PDR Minutes | Grey
2.13 | CDR Review | 14 | 2026-08-04 | 2026-08-17 | 2.9,2.12 | CAD/PM | 0% | Pending | CDR Minutes | Grey
2.14 | Phase Gate Review | 7 | 2026-11-15 | 2026-11-21 | All | Steering | 0% | Pending | Approval | Grey
PROCUREMENT TRACKER
Package | Description | RFP Date | Tender Close | Value (HK$) | Vendor | Status | RAG
PKG-001 | Primary Radar | 2026-04-15 | 2026-05-30 | 280M | TBD (Thales) | RFP Issued | Green
PKG-002 | SSR | 2026-04-15 | 2026-05-30 | 120M | TBD (Raytheon) | RFP Issued | Green
PKG-003 | MLAT | 2026-05-01 | 2026-06-15 | 45M | TBD (ERA) | Draft RFP | Amber
PKG-004 | Data Processing | 2026-05-15 | 2026-06-30 | 95M | TBD (Indra) | Planning | Grey
PKG-005 | Comms Infra | 2026-06-01 | 2026-07-15 | 35M | TBD (Nokia) | Planning | Grey
PKG-006 | Civil Works | 2026-07-01 | 2026-08-15 | 65M | TBD (Local) | Planning | Grey
PKG-007 | Installation Svc | 2026-08-01 | 2026-09-15 | 85M | TBD (SI) | Planning | Grey

## Phase 3 - Installation
PHASE 3: SITE INSTALLATION & SYSTEM INTEGRATION
WORK BREAKDOWN STRUCTURE
WBS ID | Task Name | Duration (Days) | Start | End | Predecessor | Assigned To | % Complete | Status | Deliverable | RAG | Notes
3.1 | Site Prep - Site A | 90 | 2027-01-15 | 2027-04-14 | 2.6 | Contractor | 0% | Pending | Site Ready | Grey | Chek Lap Kok
3.2 | Site Prep - Site B | 90 | 2027-01-15 | 2027-04-14 | 2.6 | Contractor | 0% | Pending | Site Ready | Grey | Tai Mo Shan
3.3 | Site Prep - Site C | 75 | 2027-02-01 | 2027-04-16 | 2.6 | Contractor | 0% | Pending | Site Ready | Grey | MLS
3.4 | Install Primary Radar | 120 | 2027-04-15 | 2027-08-12 | 3.1,PKG1 | Vendor | 0% | Pending | Install Cert | Grey
3.5 | Install SSR | 90 | 2027-05-01 | 2027-07-29 | 3.2,PKG2 | Vendor | 0% | Pending | Install Cert | Grey
3.6 | Install MLAT (x4) | 150 | 2027-04-16 | 2027-09-12 | 3.3,PKG3 | Vendor | 0% | Pending | Install Cert | Grey
3.7 | Install Data Proc | 60 | 2027-06-01 | 2027-07-30 | 3.1,PKG4 | Vendor | 0% | Pending | Install Cert | Grey
3.8 | Network Install | 75 | 2027-05-15 | 2027-07-28 | 3.1,PKG5 | Vendor | 0% | Pending | Install Cert | Grey
3.9 | System Integration | 90 | 2027-08-13 | 2027-11-10 | 3.4-3.8 | SI Lead | 0% | Pending | Integ Report | Grey
3.10 | CAD Interface | 60 | 2027-09-01 | 2027-10-30 | 3.7,3.8 | SW Team | 0% | Pending | Interface Cert | Grey | Indra system
3.11 | Power Supply | 45 | 2027-07-01 | 2027-08-14 | 3.1 | Electrical | 0% | Pending | Power Cert | Grey | UPS+Generator
3.12 | Earthing & Lightning | 30 | 2027-07-15 | 2027-08-13 | 3.1 | Electrical | 0% | Pending | Safety Cert | Grey
3.13 | Phase Gate Review | 7 | 2027-11-20 | 2027-11-26 | 3.9-3.12 | CAD/PM | 0% | Pending | Approval | Grey

## Phase 4 - Testing
PHASE 4: TESTING & COMMISSIONING
WORK BREAKDOWN STRUCTURE
WBS ID | Task Name | Duration (Days) | Start | End | Predecessor | Assigned To | % Complete | Status | Deliverable | RAG | Notes
4.1 | FAT (Factory Acceptance) | 45 | 2028-01-15 | 2028-02-27 | 3.9 | QA/Vendor | 0% | Pending | FAT Report | Grey | All subsystems
4.2 | SAT - Site A | 30 | 2028-03-01 | 2028-03-30 | 4.1 | QA Team | 0% | Pending | SAT Report A | Grey
4.3 | SAT - Site B | 30 | 2028-03-15 | 2028-04-13 | 4.1 | QA Team | 0% | Pending | SAT Report B | Grey
4.4 | SAT - Site C | 25 | 2028-04-01 | 2028-04-25 | 4.1 | QA Team | 0% | Pending | SAT Report C | Grey
4.5 | End-to-End Test | 30 | 2028-05-01 | 2028-05-30 | 4.2-4.4 | QA/PM | 0% | Pending | E2E Report | Grey | Full chain
4.6 | OAT (Operational) | 45 | 2028-06-01 | 2028-07-15 | 4.5 | CAD Ops | 0% | Pending | OAT Report | Grey | ATCO involved
4.7 | Safety Case | 30 | 2028-07-01 | 2028-07-30 | 4.6 | Safety Eng | 0% | Pending | Safety Case | Grey
4.8 | Regulatory Commissioning | 30 | 2028-08-01 | 2028-08-30 | 4.7 | CAD | 0% | Pending | Commission Cert | Grey
4.9 | Parallel Running | 90 | 2028-09-01 | 2028-11-29 | 4.8 | Ops Team | 0% | Pending | Parallel Report | Grey | 3 months
4.10 | Performance Validation | 30 | 2028-11-01 | 2028-11-30 | 4.9 | QA/PM | 0% | Pending | Perf Report | Grey | ICAO stds
4.11 | Phase Gate Review | 7 | 2028-12-05 | 2028-12-11 | 4.10 | Steering | 0% | Pending | Approval | Grey
DEFECT TRACKER
Defect ID | Description | Severity | Reported | Status | Owner | Resolution | Phase Found
DEF-001 | Radar display latency >2s | Major | 2026-03-15 | Resolved | SW Team | Algorithm fix | Phase 2
DEF-002 | SSR Mode S interrogation fail | Critical | 2026-05-20 | In Progress | Comms Eng | HW replacement | Phase 2
DEF-003 | MLAT sync drift | Minor | 2026-06-10 | Open | Nav Eng | GPS fix | Phase 2

## Phase 5 - Handover
PHASE 5: HANDOVER & PROJECT CLOSEOUT
WORK BREAKDOWN STRUCTURE
WBS ID | Task Name | Duration (Days) | Start | End | Predecessor | Assigned To | % Complete | Status | Deliverable | RAG | Notes
5.1 | System Handover | 14 | 2029-01-01 | 2029-01-14 | 4.11 | PM/Ops | 0% | Pending | Handover Cert | Grey
5.2 | Documentation Handover | 21 | 2029-01-08 | 2029-01-28 | 5.1 | Tech Writer | 0% | Pending | Doc Register | Grey | O&M manuals
5.3 | Training - ATCO | 30 | 2029-01-15 | 2029-02-13 | 5.1 | Trainer | 0% | Pending | Training Cert | Grey | 40 ATCOs
5.4 | Training - Maint Staff | 21 | 2029-01-29 | 2029-02-18 | 5.1 | Vendor | 0% | Pending | Training Cert | Grey | 25 engineers
5.5 | Training - Eng Staff | 14 | 2029-02-19 | 2029-03-04 | 5.1 | Vendor | 0% | Pending | Training Cert | Grey | 15 engineers
5.6 | Warranty Period Start | 182 | 2029-01-15 | 2029-07-15 | 5.1 | PM | 0% | Pending | Warranty Cert | Grey | 24 months
5.7 | Final Documentation | 30 | 2029-02-01 | 2029-03-02 | 5.2 | PM | 0% | Pending | Final Package | Grey | As-built
5.8 | Financial Closeout | 21 | 2029-03-15 | 2029-04-04 | 5.7 | Finance | 0% | Pending | Final Account | Grey | All payments
5.9 | Lessons Learned Workshop | 7 | 2029-04-05 | 2029-04-11 | 5.8 | PM | 0% | Pending | LL Report | Grey | All phases
5.10 | Final Audit | 14 | 2029-04-12 | 2029-04-25 | 5.9 | Auditor | 0% | Pending | Audit Report | Grey | Independent
5.11 | Project Closure | 7 | 2029-06-24 | 2029-06-30 | 5.10 | PM | 0% | Pending | Closure Report | Grey

## KPI & PMP Summary
CONSOLIDATED KPI & PMP MEASUREMENTS
PMP KNOWLEDGE AREA COMPLIANCE
Knowledge Area | Process Group | Key Deliverable | Status | Compliance % | Auditor Notes
Integration | All Phases | Project Mgmt Plan | On Track | 95% | PMBOK 7
Scope | Planning | WBS / Reqs Doc | On Track | 98% | 215 reqs
Schedule | Plan/Monitor | Gantt / Milestones | On Track | 92% | 12 milestones
Cost | Plan/Monitor | Budget / EVM | On Track | 96% | CPI=1.05
Quality | Executing | QA Plan / Defects | On Track | 94% | ISO 9001
Resource | Executing | Resource Histogram | On Track | 90% | 52 FTEs
Communications | All | Comms Plan / Reports | On Track | 95% | Weekly
Risk | Plan/Monitor | Risk Register | On Track | 92% | 68 risks
Procurement | Plan/Exec | Contracts / POs | On Track | 88% | 7 packages
Stakeholder | All | Stakeholder Register | On Track | 97% | 47 stakeholders
EARNED VALUE MANAGEMENT DETAIL
Month | PV | EV | AC | SV | CV | SPI | CPI
Jul-25 | 3.5 | 3.3 | 3.2 | -0.2 | 0.1 | 0.943 | 1.031
Aug-25 | 7.1 | 6.8 | 6.5 | -0.3 | 0.3 | 0.958 | 1.046
Sep-25 | 12.8 | 12.2 | 11.5 | -0.6 | 0.7 | 0.953 | 1.061
Oct-25 | 18.5 | 17.8 | 16.8 | -0.7 | 1 | 0.962 | 1.06
Nov-25 | 25 | 24 | 22.8 | -1 | 1.2 | 0.96 | 1.053
Dec-25 | 32.5 | 31 | 29.5 | -1.5 | 1.5 | 0.954 | 1.051
Jan-26 | 42.5 | 40.5 | 38.5 | -2 | 2 | 0.953 | 1.052
Feb-26 | 54 | 51.5 | 49 | -2.5 | 2.5 | 0.954 | 1.051
Mar-26 | 66.5 | 63.5 | 60.5 | -3 | 3 | 0.955 | 1.05
Apr-26 | 80 | 76.5 | 73 | -3.5 | 3.5 | 0.956 | 1.048
May-26 | 95 | 91 | 86.5 | -4 | 4.5 | 0.958 | 1.052
Jun-26 | 110 | 105.5 | 101 | -4.5 | 4.5 | 0.959 | 1.045
BUDGET BREAKDOWN BY PHASE
Phase | Budget | Committed | Spent | Remaining | % Spent | EAC | Variance | Risk Reserve
Phase 1 | 42.5M | 42.5M | 38.2M | 4.3M | 90% | 40.5M | +2.0M | 2.1M
Phase 2 | 170M | 110M | 95M | 75M | 56% | 165M | +5.0M | 8.5M
Phase 3 | 340M | 0 | 0 | 340M | 0% | 340M | 0 | 17.0M
Phase 4 | 127.5M | 0 | 0 | 127.5M | 0% | 125M | +2.5M | 6.4M
Phase 5 | 170M | 0 | 0 | 170M | 0% | 170M | 0 | 8.5M
TOTAL | 850M | 152.5M | 133.2M | 716.8M | 16% | 840.5M | +9.5M | 42.5M

## Risk Register
PROJECT RISK REGISTER
Risk ID | Description | Category | Prob (1-5) | Impact (1-5) | Score | Mitigation | Owner | Status | Phase | Updated
R-001 | Radar delivery delayed | Schedule | 3 | 4 | 12 | Dual-source | Procurement | Active | Phase 2 | 2026-05-01
R-002 | Site access restrictions | Schedule | 2 | 5 | 10 | Early coordination | Site Mgr | Active | Phase 3 | 2026-04-15
R-003 | Currency fluctuation | Financial | 3 | 3 | 9 | Forward contracts | Finance | Active | Phase 2 | 2026-05-10
R-004 | Key personnel unavail | Resource | 2 | 4 | 8 | Cross-training | HR | Monitoring | All | 2026-03-20
R-005 | Regulatory approval delay | Schedule | 3 | 5 | 15 | Early engagement | PM | Active | Phase 2 | 2026-05-01
R-006 | Legacy CAD integration | Technical | 4 | 4 | 16 | Early prototyping | SW Arch | Active | Phase 2-3 | 2026-04-01
R-007 | Underground utilities | Technical | 2 | 4 | 8 | GPR survey | Civil | Monitoring | Phase 3 | 2026-04-20
R-008 | Weather delays | Schedule | 3 | 3 | 9 | Schedule buffer | Site Mgr | Monitoring | Phase 3 | 2026-03-15
R-009 | Cybersecurity cert delay | Technical | 2 | 4 | 8 | Early CERT engagement | IT Security | Monitoring | Phase 4 | 2026-05-05
R-010 | Stakeholder opposition | Stakeholder | 1 | 3 | 3 | Public consultation | PM | Closed | Phase 1 | 2025-09-10

## Issue Log
PROJECT ISSUE LOG
Issue ID | Description | Raised Date | By | Priority | Status | Assigned To | Due Date | Resolution | Phase
ISS-001 | SSR vendor criteria disputed | 2026-04-10 | PM | High | In Progress | Procurement | 2026-05-30 | Clarification meeting | Phase 2
ISS-002 | Site B access road inadequate | 2026-03-25 | Site Eng | Medium | Open | Civil Works | 2026-06-15 | Road upgrade quote | Phase 2
ISS-003 | Radar frequency conflict | 2026-05-01 | Comms Eng | High | In Progress | Tech Lead | 2026-05-20 | OFCA coordination | Phase 2
ISS-004 | CAD ops unavailable for OAT | 2026-04-20 | QA | Medium | Open | PM | 2026-06-30 | Schedule meeting | Phase 4
ISS-005 | PKG-001 budget overrun risk | 2026-05-15 | Cost Eng | High | Under Review | Finance | 2026-06-15 | Value engineering | Phase 2

## Change Requests
CHANGE REQUEST LOG
CR ID | Description | Requestor | Submitted | Cost Impact | Schedule Impact | Priority | Status | Decision Date | Approved By
CR-001 | Add 5th MLAT station | CAD Ops | 2026-04-01 | +12M | +45 days | Medium | Approved | 2026-05-10 | Steering Comm
CR-002 | Upgrade display to 4K | ATCO Union | 2026-03-15 | +3.5M | +14 days | Low | Approved | 2026-04-20 | PM
CR-003 | Cybersecurity requirements | IT Security | 2026-05-05 | +8M | +30 days | High | Under Review | — | —
CR-004 | Extend parallel running | CAD Ops | 2026-04-20 | +5M | +90 days | Medium | Pending | — | —